## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Requirement Analysis & Scope Definition | MUST HAVE | No Dependency | Deepika, Ananya, Kaliyappan | 3 - Completed
S1 | S1 | US-002 | Finalize Technology Stack (Python, Dash, Plotly, MongoDB) | MUST HAVE | Project Requirement Analysis | Roshini, Apurva, Sai Durga | 3 - Completed
S1 | S1 | US-003 | System Architecture Design | MUST HAVE | Technology Stack Finalization | Roshini, Apurva, Sai Durga | 3 - Completed
S1 | S1 | US-004 | GitHub Repository & Project Structure Setup | MUST HAVE | System Architecture Design | Javeed, Sunez, Sandhya | 3 - Completed
S2 | S2 | US-005 | Data Schema Design & Pydantic Models | MUST HAVE | GitHub & Project Setup | Roshini, Apurva, Sai Durga | 3 - Completed
S2 | S2 | US-006 | MongoDB Atlas Configuration & Query Helpers | MUST HAVE | Data Schema Design | Roshini, Apurva, Sai Durga | 3 - Completed
S2 | S2 | US-007 | NVD CVE Feed Ingestion Module | MUST HAVE | MongoDB Configuration | Deepika, Ananya, Kaliyappan | 3 - Completed
S3 | S3 | US-008 | AbuseIPDB Malicious IP Feed Integration | MUST HAVE | NVD Ingestion Module | Deepika, Ananya, Kaliyappan | 3 - Completed
S3 | S3 | US-009 | AlienVault OTX Threat Pulse Integration | MUST HAVE | API Key Configuration | Deepika, Ananya, Kaliyappan | 3 - Completed
S3 | S3 | US-010 | Simulated Threat Data Generator | MUST HAVE | Data Schema Design | Deepika, Ananya, Kaliyappan | 3 - Completed
S3 | S3 | US-011 | Master Ingestion Orchestrator (fetch_all) | MUST HAVE | All Ingestion Modules | Deepika, Ananya, Kaliyappan | 3 - Completed
S3 | S3 | US-012 | GeoIP Enrichment Engine (ip-api.com) | MUST HAVE | AbuseIPDB Integration | Roshini, Apurva, Sai Durga | 3 - Completed
S4 | S4 | US-013 | MITRE ATT&CK Threat Categorization Mapping | MUST HAVE | Ingestion Orchestrator | Roshini, Apurva, Sai Durga | 3 - Completed
S4 | S4 | US-014 | ML Service – Severity Prediction (FastAPI) | MUST HAVE | Threat Categorization | Annas, Vibhushana, Shrusti | 3 - Completed
S4 | S4 | US-015 | ML Service – Anomaly Detection & Batch Scoring | MUST HAVE | ML Severity Prediction | Annas, Vibhushana, Shrusti | 3 - Completed
S4 | S4 | US-016 | Alert Engine – Telegram & Email Notifications | MUST HAVE | Anomaly Detection Module | Javeed, Sunez, Sandhya | 3 - Completed
S5 | S5 | US-017 | Time-Series & Trend Charts | MUST HAVE | MongoDB Query Helpers | Annas, Vibhushana, Shrusti | 3 - Completed
S5 | S5 | US-018 | Geospatial Threat Map – Choropleth & Scatter Geo | MUST HAVE | GeoIP Enrichment Engine | Annas, Vibhushana, Shrusti | 3 - Completed
S5 | S5 | US-019 | Treemap / Sunburst – MITRE Hierarchy Visualization | MUST HAVE | MITRE ATT&CK Mapping | Annas, Vibhushana, Shrusti | 3 - Completed
S5 | S5 | US-020 | Threat Intelligence Tab – IOC Lookup & OTX Pulses | MUST HAVE | AbuseIPDB & OTX Integrations | Annas, Vibhushana, Shrusti | 3 - Completed
S5 | S5 | US-021 | Network Scanner Module (Nmap) | MUST HAVE | Backend Services Setup | Javeed, Sunez, Sandhya | 3 - Completed
S5 | S5 | US-022 | URL / QR Code Scanner Module | MUST HAVE | Backend Services Setup | Javeed, Sunez, Sandhya | 3 - Completed
S5 | S5 | US-023 | GitHub Actions Cron Scheduler (15-min ingestion) | MUST HAVE | Ingestion Orchestrator | Deepika, Ananya, Kaliyappan | 3 - Completed
S5 | S5 | US-024 | Dash Application Integration & Interactive Filters | MUST HAVE | All Visualization Modules | Javeed, Sunez, Sandhya | 3 - Completed
S5 | S5 | US-025 | Executive Report Generator | SHOULD HAVE | Dashboard Integration | Annas, Vibhushana, Shrusti | 3 - Completed
S5 | S5 | US-026 | Render.com Cloud Deployment & Environment Config | MUST HAVE | Dash Application | Javeed, Sunez, Sandhya | 3 - Completed
S5 | S5 | US-027 | System Testing, Bug Fixes & Performance Tuning | MUST HAVE | Complete Integrated System | Javeed, Sunez, Sandhya | 3 - Completed
S5 | S5 | US-028 | Agile Documentation Preparation | MUST HAVE | Sprint Records | Annas, Vibhushana, Shrusti | 3 - Completed

## Sprint Backlog
[8 empty] | 217 | 6 | 8 | 7 | 5 | 5 | 1 | 6 | 9 | 9 | 5 | 2 | 0 | 10 | 12 | 11 | 7 | 4 | 1 | 0 | 5 | 11 | 12 | 10 | 6 | 3 | 0 | 10 | 17 | 20 | 19 | 20 | 21 | 18
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33
US-001 | T-001 | Gather project objectives and define functional requirements | 2026-02-11 | 2026-02-12 | Deepika | Planning | 3 - Completed | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Identify data sources: NVD, AbuseIPDB, OTX, Simulated | 2026-02-11 | 2026-02-12 | Ananya | Planning | 3 - Completed | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-003 | Create project scope document and module breakdown | 2026-02-12 | 2026-02-12 | Kaliyappan | Planning | 3 - Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-004 | Evaluate Python/Dash/Plotly vs alternative stacks | 2026-02-12 | 2026-02-13 | Roshini | Planning | 3 - Completed | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-005 | Finalize stack: Python, Dash, Plotly, MongoDB Atlas | 2026-02-13 | 2026-02-13 | Apurva | Planning | 3 - Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-006 | Design layered architecture diagram (4 modules) | 2026-02-13 | 2026-02-14 | Roshini | Planning | 3 - Completed | 3 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-007 | Define data flow: APIs → ingestion → MongoDB → dashboard | 2026-02-13 | 2026-02-14 | Sai Durga | Planning | 3 - Completed | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-008 | Initialize GitHub repo and define folder structure | 2026-02-14 | 2026-02-15 | Javeed | Setup | 3 - Completed | 2 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-009 | Setup .env, requirements.txt, .gitignore | 2026-02-15 | 2026-02-15 | Sandhya | Setup | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-010 | Configure environment settings and constants | 2026-02-15 | 2026-02-16 | Sunez | Setup | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-011 | Design ThreatEvent Pydantic schema | 2026-02-17 | 2026-02-17 | Apurva | Setup | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-012 | Design CVEEvent and GeoLocation models | 2026-02-17 | 2026-02-18 | Roshini | Setup | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-013 | Connect to MongoDB Atlas (M0 free tier) | 2026-02-18 | 2026-02-18 | Sai Durga | Setup | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-014 | Build aggregate query helpers for dashboard | 2026-02-18 | 2026-02-19 | Roshini | Setup | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-015 | Create and verify MongoDB indexes | 2026-02-19 | 2026-02-19 | Sai Durga | Setup | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-016 | Implement NVD CVE API fetcher with rate-limit handling | 2026-02-19 | 2026-02-20 | Kaliyappan | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-017 | Normalize CVE data to ThreatEvent schema | 2026-02-20 | 2026-02-21 | Deepika | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-018 | Integrate AbuseIPDB blacklist API | 2026-02-23 | 2026-02-24 | Ananya | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-019 | Parse AbuseIPDB response and store to MongoDB | 2026-02-24 | 2026-02-24 | Kaliyappan | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-020 | Integrate AlienVault OTX pulse feed | 2026-02-23 | 2026-02-24 | Deepika | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-021 | Map OTX data to ThreatEvent model | 2026-02-25 | 2026-02-25 | Ananya | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-022 | Build simulate_data.py with realistic distributions | 2026-02-24 | 2026-02-25 | Kaliyappan | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-023 | Generate 500+ simulated events for dev/demo | 2026-02-25 | 2026-02-25 | Deepika | Coding | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-024 | Build fetch_all.py master orchestrator | 2026-02-25 | 2026-02-26 | Ananya | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-025 | Add error isolation per source in orchestrator | 2026-02-26 | 2026-02-26 | Kaliyappan | Coding | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-026 | Integrate ip-api.com for GeoIP country/city lookup | 2026-02-26 | 2026-02-27 | Apurva | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-027 | Attach latitude/longitude to each ThreatEvent | 2026-02-27 | 2026-02-28 | Sai Durga | Coding | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-028 | Map attack types to MITRE ATT&CK techniques | 2026-03-02 | 2026-03-03 | Roshini | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-029 | Validate MITRE tactic/technique categorization | 2026-03-03 | 2026-03-03 | Apurva | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-030 | Train ML severity prediction model (Random Forest) | 2026-03-03 | 2026-03-04 | Annas | Coding | 3 - Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-031 | Expose /predict endpoint via FastAPI | 2026-03-04 | 2026-03-04 | Vibhushana | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-032 | Build /anomaly/batch endpoint for hourly count scoring | 2026-03-04 | 2026-03-05 | Shrusti | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-033 | Add /classify attack type endpoint | 2026-03-05 | 2026-03-05 | Annas | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-034 | Implement Telegram bot alert delivery | 2026-03-05 | 2026-03-06 | Javeed | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-035 | Implement Email (SendGrid/SMTP) alert delivery | 2026-03-06 | 2026-03-06 | Sandhya | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-036 | Add alert deduplication and cooldown logic | 2026-03-07 | 2026-03-07 | Sunez | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T-037 | Build time-series chart for attack frequency | 2026-03-09 | 2026-03-09 | Vibhushana | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T-038 | Build severity distribution bar chart | 2026-03-09 | 2026-03-10 | Shrusti | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US-017 | T-039 | Build attack-type donut and heatmap charts | 2026-03-09 | 2026-03-10 | Annas | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US-018 | T-040 | Build Plotly choropleth world threat map | 2026-03-10 | 2026-03-10 | Vibhushana | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-018 | T-041 | Add scatter-geo overlay for individual IP incidents | 2026-03-10 | 2026-03-11 | Shrusti | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0
US-019 | T-042 | Build treemap chart for MITRE tactic breakdown | 2026-03-10 | 2026-03-11 | Annas | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0
US-019 | T-043 | Build sunburst chart for tactic→technique hierarchy | 2026-03-11 | 2026-03-11 | Vibhushana | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-020 | T-044 | Build IOC lookup panel (AbuseIPDB + OTX) | 2026-03-11 | 2026-03-12 | Shrusti | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0
US-020 | T-045 | Display recent OTX pulses and top reported IPs | 2026-03-11 | 2026-03-12 | Annas | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0
US-021 | T-046 | Develop Nmap network scanner integration | 2026-03-11 | 2026-03-12 | Javeed | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0
US-021 | T-047 | Display scan results on dashboard security tools tab | 2026-03-12 | 2026-03-12 | Sandhya | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-022 | T-048 | Build URL maliciousness scanner module | 2026-03-12 | 2026-03-12 | Sunez | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
US-022 | T-049 | Add QR code decode and scan pipeline | 2026-03-12 | 2026-03-13 | Javeed | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
US-023 | T-050 | Configure GitHub Actions cron workflow | 2026-03-12 | 2026-03-13 | Deepika | Setup | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
US-023 | T-051 | Add GitHub Secrets for API keys and MONGO_URI | 2026-03-13 | 2026-03-13 | Ananya | Setup | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US-024 | T-052 | Integrate all visualizations into Dash app.py | 2026-03-13 | 2026-03-13 | Javeed | Coding | 3 - Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
US-024 | T-053 | Add interactive filters (date range, severity, country) | 2026-03-13 | 2026-03-14 | Sandhya | Coding | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0
US-024 | T-054 | Apply custom CSS for alerts panel and dropdowns | 2026-03-13 | 2026-03-14 | Sunez | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0
US-025 | T-055 | Build report generator for PDF/HTML export | 2026-03-14 | 2026-03-14 | Vibhushana | Coding | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
US-025 | T-056 | Format executive summary with top CVEs and risk profile | 2026-03-14 | 2026-03-14 | Shrusti | Coding | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-026 | T-057 | Configure render.yaml for Render.com web service | 2026-03-14 | 2026-03-14 | Javeed | Setup | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-026 | T-058 | Set all production environment variables on Render | 2026-03-14 | 2026-03-15 | Sandhya | Setup | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
US-027 | T-059 | Perform end-to-end integration testing on all modules | 2026-03-14 | 2026-03-15 | Sunez | Testing | 3 - Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2
US-027 | T-060 | Fix bugs identified during integration testing | 2026-03-15 | 2026-03-15 | Javeed | Testing | 3 - Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
US-027 | T-061 | Optimize MongoDB queries and dashboard load time | 2026-03-15 | 2026-03-15 | Sandhya | Testing | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-028 | T-062 | Prepare Product Backlog and Sprint Backlog sheets | 2026-03-15 | 2026-03-15 | Vibhushana | Documentation | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-028 | T-063 | Record Stand-up meetings and Retrospection data | 2026-03-15 | 2026-03-15 | Annas | Documentation | 3 - Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-028 | T-064 | Finalize and review complete Agile documentation | 2026-03-15 | 2026-03-15 | Shrusti | Documentation | 3 - Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2

## Stand up Meeting
Sprint | Day | Impediment / Issue | Action Taken
Sprint 1 | Day 2 (12-Feb) | Uncertainty in deciding the final Python dashboard framework (Dash vs Streamlit) | Team compared both frameworks; agreed on Plotly Dash for native Plotly integration and richer interactivity.
Sprint 1 | Day 4 (14-Feb) | Confusion around layered architecture and boundaries between the 4 modules | Conducted whiteboard session; finalized ingestion → processing → storage → dashboard flow with clear module ownership.
Sprint 1 | Day 6 (16-Feb) | Difficulty setting up MongoDB Atlas M0 free tier and obtaining the connection string | Followed official Atlas documentation step-by-step; verified connection using a PyMongo test script before proceeding.
Sprint 2 | Day 8 (18-Feb) | Pydantic schema validation errors when normalising NVD CVE response fields to ThreatEvent model | Debugged field type mismatches; updated ThreatEvent to handle optional fields with safe default values.
Sprint 2 | Day 10 (20-Feb) | NVD API rate limiting causing incomplete CVE fetch runs during testing | Implemented request delay and retry logic in fetch_nvd.py; reduced redundant calls by caching recent results locally.
Sprint 2 | Day 12 (22-Feb) | Inconsistent JSON response structures returned by NVD, AbuseIPDB, and OTX APIs | Built per-source normalizer functions that map raw API fields to the unified ThreatEvent schema before MongoDB insertion.
Sprint 2 | Day 14 (24-Feb) | AbuseIPDB returning incomplete or missing geolocation data for several IPs | Added ip-api.com as a secondary GeoIP resolver in fetch_abuseipdb.py with fallback logic for missing location fields.
Sprint 3 | Day 15 (25-Feb) | AlienVault OTX pulse payload too large, significantly slowing ingestion run duration | Added pagination control and filtered to only recent pulses (last 7 days) in fetch_otx.py to reduce payload size.
Sprint 3 | Day 17 (27-Feb) | Simulated data generator producing unrealistic geographic and attack-type distributions | Revised simulation weights in simulate_data.py using real-world attack origin statistics; rebalanced country and type frequency.
Sprint 3 | Day 19 (01-Mar) | fetch_all.py orchestrator failing silently when one data source raised an unhandled exception | Wrapped each source call in isolated try/except with detailed logging; one source failure no longer halts remaining sources.
Sprint 3 | Day 21 (03-Mar) | MongoDB aggregate query helpers returning stale or incorrect counts under certain filter combinations | Reviewed and corrected aggregation pipeline stages in database.py; added index verification to ensure query performance.
Sprint 4 | Day 22 (04-Mar) | ML model training failing due to severely imbalanced severity class labels in training data | Applied class_weight='balanced' in scikit-learn Random Forest; re-evaluated with stratified cross-validation splits.
Sprint 4 | Day 24 (06-Mar) | FastAPI ML microservice returning CORS errors when called from the Dash dashboard | Added CORSMiddleware to ml_service/main.py with appropriate allowed origins; verified fix via browser network inspector.
Sprint 4 | Day 25 (07-Mar) | Telegram alert bot not firing during low-activity test periods due to threshold not being crossed | Lowered threshold values temporarily in .env for testing; confirmed bot token and TELEGRAM_CHAT_ID were correctly set.
Sprint 4 | Day 26 (08-Mar) | Alert engine in alert_engine.py re-firing duplicate alerts within the cooldown window | Fixed deduplication logic using alert hash and ALERT_COOLDOWN_MINUTES check against MongoDB alert records.
Sprint 5 | Day 28 (10-Mar) | Plotly choropleth map rendering slowly with large country-count datasets from MongoDB | Moved country aggregation to the MongoDB query layer in database.py; only pre-aggregated totals sent to build_choropleth_map().
Sprint 5 | Day 30 (12-Mar) | Treemap and sunburst charts not reflecting MITRE ATT&CK hierarchy correctly for some techniques | Fixed parent-child label mapping in geo_charts.py; cross-referenced against MITRE ATT&CK v14 dataset to validate categories.
Sprint 5 | Day 33 (15-Mar) | Dash callback errors triggered when multiple filter dropdowns (hours, attack type, severity) changed simultaneously | Refactored into a single combined callback in app.py accepting all filter inputs; eliminated circular dependency warnings.

## Retrospection
Sprint # | Sprint | Start Date | End Date | Team Members | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 11-Feb-2026 | 16-Feb-2026 | Deepika Koli, Ananya, Kaliyappan S | Document architecture decisions and share diagrams before coding begins | Starting implementation before finalizing environment and repo structure | Daily planning calls and shared Notion board for task tracking | Finalized architecture diagram, resolved Git conflicts, standardized .env setup
2 | Sprint 2 | 17-Feb-2026 | 22-Feb-2026 | Roshini Chavala, Sai Durga Prasad, Apurva | Implement API caching and rate-limit handling from the start of each integration | Making API calls without testing edge cases and error boundaries first | Pair programming on backend modules and daily API integration reviews | Added request caching, fixed JWT refresh flow, redesigned MongoDB schema with indexes
3 | Sprint 3 | 23-Feb-2026 | 01-Mar-2026 | Annas, Vibhushana Baskar, Shrusti M | Use virtualization and lazy loading for data-heavy UI components | Rendering full datasets without pagination during live demo testing | Cross-team code reviews before merging frontend feature branches | Optimized Socket.IO load handling, added chart virtualization, improved map clustering
4 | Sprint 4 | 02-Mar-2026 | 15-Mar-2026 | Mohamed Javeed, Sunez Afza, Sandhya Sagala | Write integration tests alongside feature development, not just at the end | Ignoring edge-case validation in scan and AI modules | Sprint demo reviews with all team members before final release | Fixed MITRE mapping accuracy, secured RAG pipeline, resolved all Docker env issues, passed final QA